# iCFO Virtual Private Equity Expo — Dry Run Checklist

Sandbox event:  DRY RUN — [date]  (Duplicate of the live event; visibility = Members only / Draft)

Rehearsal time:  [same time of day as the real event]      Timezone: [e.g. America/Los_Angeles — PDT]

Director:  [name] — runs the Manage screen, cues go-live, handles issues

Rehearse on the duplicated event, never the live one. Run it at the same time of day a few days out to catch timezone, link-expiry, and A/V issues.

## 1 · Roles (assign before you start)

| Role | Person | Notes |
| --- | --- | --- |
| Director / producer |  | Watches Manage, cues go-live, handles issues |
| Host & moderator |  | Talk Show host, welcomes attendees |
| Keynote speaker |  | Auditorium |
| Panelists x4 |  | Talk Show guest roster |
| Featured founder (CEO) |  | VIP Room / Founder Showcase |
| Test attendees x2-3 |  | Join on different devices / browsers |

## 2 · Setup (do once, before the team joins)

☐  Duplicated the live event → renamed “DRY RUN — [date]”

☐  Visibility set to Members only, or left as Draft

☐  Event date/time + timezone correct on the public page (“Add to calendar” lands right)

☐  Sessions present and in the right running order (drag to reorder)

☐  Each session's live link added and opens

☐  Talk Show Guest Roster pre-loaded (Host, CEO, Panelists 1–4)

☐  Sponsors / banners showing correctly in the lobby

## 3 · Individual tech check (each presenter, ~5 min — BEFORE the full run)

☐  Presenter can reach the event and Enter lobby

☐  Opens their session live link; camera + mic work

☐  Screen share works (slides / demo)

☐  Audio levels good, no echo; lighting acceptable

☐  Knows how to Open live link and End session

☐  Backup: presenter has the link saved separately in case the tab closes

## 4 · Full run-of-show (real time, everyone in)

| Time | Segment | Owner | Verify |
| --- | --- | --- | --- |
| T-15 | Doors open / Lobby | Director | Register → Enter lobby; presence count rises; booths clickable |
| T-0 | Welcome | Host | Lobby ticker + welcome; wave/greeting works |
| +2 | Keynote (Auditorium) | Director / Speaker | Go live on Main Stage; attendees see stream; end cleanly |
| +20 | Talk Show — Inside the Investor's Mind | Host | Bring on each panelist; tiles appear; remove/re-add works |
| +40 | Workshops (Exhibitors / Community) | Owners | Sessions go live; switching rooms works |
| +55 | Founder Showcase (VIP Room) | CEO | HealthTech session live; sector track shows |
| +70 | Networking + Expo Hall | All | Lounge / booths reachable; sponsor pages load |
| +85 | Close | Host | End sessions; thank-yous; on-demand / recording note |

## 5 · Attendee-experience checks (from the test attendees' side)

☐  Presence: avatar shows; hover shows name; count is accurate

☐  Lobby navigation works on desktop and mobile

☐  Live poll appears and records a vote

☐  Timezone shows correctly for an attendee in another zone

☐  Chat / wave / “Say hi” reaches the right person

☐  Leaderboard updates

## 6 · Failure drills (practice these — they happen live)

☐  Speaker's live link dies → End session and relaunch with a fresh link

☐  Disruptive attendee → mute / move / remove from the control screen

☐  Host hand-off → second host can take over moderation

☐  Stream lag → fallback message / switch to backup link

## 7 · Debrief (right after)

☐  Log every issue with who / what / fix

☐  Apply the needed fixes on the LIVE event (not the sandbox)

☐  Confirm final running order and all live links for event day

☐  Archive or delete the DRY RUN copy when done

Sign-off:   Director __________     Host __________     Tech __________